## Project Roadmap
Hospital Information Dashboard
Marketing Plan Lists |  | Status Color Legend & Toggle
|  | Not Started | In Progress | Delayed | Complete | Custom 1 | Custom 2 | Custom 3 | Custom 4
|  | ON | ON | ON | ON | OFF | OFF | OFF | OFF
Task | Status | Anticipated Start Date | Anticipated End Date | Actual Start Date | Actual End Date
Select Project | Complete | 2019-03-22 | 2019-03-31 | 2019-03-22 | 2019-04-05
Set up Repository in Github | Complete | 2019-03-22 | 2019-03-31 | 2019-03-22 | 2019-04-05
Create ReadMe File | Complete | 2019-03-31 | 2019-04-12 | 2019-04-05 | 2019-04-05
Select datasets | In Progress
Research python libraries required | In Progress | 2019-04-08 | 2019-04-15
Locate learnng tools for required libraries | In Progress
Review pandas | Not Started | 2019-04-14 | 2019-04-19 | 2019-04-14
Review numpy | Not Started | 2019-04-14 | 2019-04-19
Review matplotlib | Not Started | 2019-04-14 | 2019-04-19
Review plotly and dash | Not Started | 2019-04-14 | 2019-04-19
Test cms scrape code from data world | Not Started
Test pandas import | Not Started
Test and choose graphics package | Not Started
Show data on local host or use flask as webpage | Not Started
Go to list of web links

## Links
Web Links
Marketing Plan Data
Description | URL
Google Cloud | https://cloud.google.com/bigquery/docs/bigquery-storage-python-pandas
Go to Project Road Map